## Contacts List
Resource Name | Organization | Project Role | Office Phone | Cell Phone | Time Zone | Email Address
Client Project Team
Patsy Floyd | Daviess | PM | 812-254-2760 ext 1222 | 270-399-0420 | EST | pfloyd@dchosp.org
Debbie Hill | Daviess | Analyst / Builder | 812-254-2760 ext 1148 |  | EST | dhill@dchosp.org
Heather Alwell | Daviess | Analyst / Builder | 812-254-2760 ext 1209 | 586-522-6190 | EST | halwell@dchosp.org
Rex Fleetwood | Daviess | I.T. Manager | 812.254-2760 ext 1211 | 812-257-4268 | EST | rfleetwood@dchosp.org
Zach Hopper | Daviess | Technical Resource | 812-254-2760 ext 1212 | 812-582-1139 |  | zhopper@dchosp.org
Go-Live Direct Line to call: ext 5483 (Live)
Altera Project Team
Suhel Sumra | Altera | Paragon Services PM |  |  |  | suhel.sumra@allscripts.com
Robert Acevedo | Altera | Hosting PM |  |  |  | robert.acevedo@allscripts.com
Heather Rowda | Altera | Technical Account Manager (TAM) |  |  |  | heather.rowda@allscripts.com
Kevin Clayton | Altera | Client Account Manager |  |  |  | kevin.clayton@allscripts.com
Jim Owens | Altera | AOE |  |  |  | jim.owens@allscripts.com
Nikita Mathur | Altera | Implementation Consultant - ORM |  |  |  | nikita.mathur@allscripts.com
Trina Daywalt | Altera | Implementation Consultant - Pharmacy |  |  |  | trina.daywalt@allscripts.com
Trina Daywalt | Altera | Implementation Consultant - Rules Engine |  |  |  | trina.daywalt@allscripts.com
Sharon Thomas- Moore | Altera | Implementation Consultant - RCM |  |  |  | sharon.thomas-moore@allscripts.com
Fredy Ortegon | Altera | Implementation Consultant - Gen Finance |  |  |  | fredy.ortegon@allscripts.com
Ketsia Simeus | Altera | Implementation Consultant - Clinical |  |  |  | ketsia.simeus@allscripts.com
Catherine Garner | Altera | Implementation Consultant - Lab/Rad |  |  |  | catherine.garner@allscripts.com
Anita Bennett | Altera | Implementation Consultant - ClinDoc |  |  |  | anita.bennett@allscripts.com
Ashwini Patil | Altera | Integration Analyst (On Call) |  |  |  | ashwini.patil@allscripts.com
Fatmata Enyi | Altera | Implementation Support Consultant (Primary) |  |  |  | fatmata.enyi@allscripts.com
Courtney Privett | Altera | Implementation Support Consultant |  |  |  | courtney.privett@allscripts.com
TBD | Altera | Hosting Infrastructure / Citrix Engineer
Chon Phoung | Altera | System Engineer - Hosting |  |  |  | chon.phuong@alterahealth.com
Nancy Tyree | Altera | System Engineer - Primary (Paragon) |  |  |  | nancy.tyree@allscripts.com
Justin Peterson | Altera | System Engineer - Ancillary (Paragon) |  |  |  | justin.peterson@alterahealth.com
Heather Hosier | Altera | System Engineer - Post Checkout Support |  |  |  | heather.hosier@alterahealth.com

## Master Go Live Plan by Time
|  | 2022-08-10 01:00 |  | Eastern Time Zone
Phase | Status | Approximate Start Time | FORMULA | Estimated Duration | Task Name | Responsibility | Dependency | Status | Comments/ Notes
Go-Live Prep |  | 2022-07-20 01:00 | #N/A |  | Discuss SSIS data base and custom reports. If site has them they need a backup of the reports and the SQL data base moved over from current prod to pre prod | Suhel Sumra
Go-Live Prep |  | 2022-07-20 01:00 | #N/A |  | Verify PI Reporting has been tested | Suhel Sumra
Go-Live Prep |  | 2022-07-20 01:00 | #N/A |  | Discuss plan for Closing jobs: What time will it be run? How many jobs will be completed before the downtime? Will there be any jobs to be completed after the system is back up? | Suhel Sumra |  | Completed | HPF – Transfer FMR – starts at 1am and finishes around 5;15am MAR – Transfer MedAdmin – starts at 3:15am and finishes around 5am COE- Transfer CPOE Orders – starts at 1am and finishes in 5-10 minutes MRR – Transfer MedRecon – starts at 1am and finishes about 1:15am PAT – Transfer Patient Profile – starts at 7:30am and finishes in a couple minutes Paragon Tech will run the jobs manually which are not run during closing & will start manually.
Go-Live Prep |  | 2022-07-20 01:00 |  |  | Confirm PACS has been tested and any steps necessary to activate (i.e. rebooting, recycling, etc.) have been added to their live steps. | Suhel Sumra |  | Not Tested | To be completed at least 3 weeks prior to activation
Go-Live Prep |  | 2022-07-20 01:00 |  |  | Confirm whether any additional IT work or upgrades are planned during downtime for the upgrade. | Suhel Sumra |  | No | Goal is to not have any additional activities that are not required or related to the upgrade.
Go-Live Prep |  | 2022-07-27 01:00 | #N/A |  | Set up call with Primary Tech to compare timing and software, bundles and WI to be installed. If Remote Hosted, include Hosting PM and Citrix resource. | Suhel Sumra |  | Completed | Suhel to check notes for standalone
Go-Live Prep |  | 2022-07-27 01:00 | #N/A |  | Open Change Request for Production upgrade in ServiceNow (Chon will make sure blackout is in place when putting it in change request) | Chon Phuong |  |  | Chon will have RFC by 8/5/2022
Go Live Prep |  | 2022-07-27 01:00 |  |  | Confirm the Citrix Receiver version on the client devices are aligned with Paragon requirements. (See Hardware requirements document from Altera Central.) | Client |  | Not upgraded | Still working on it.
Go-Live Prep |  | 2022-07-27 01:00 | #N/A |  | Client to Ensure they have access to all areas that have tracking boards - will need to power off before the upgrade starts | Client |  |  | Needed for shutting down tracking boards if customers have tracking boards set to auto-login; otherwise, they will log right back in.
Go-Live Prep |  | 2022-07-27 01:00 | #N/A |  | Review standalone fix list and record actual installs to those delivered. Provide final list to Primary Tech. Confirm the list with the Client as well. | Suhel Sumra |  | Completed | Complete at least 2 weeks prior to Upgrade, no later than 4 business days prior to upgrade.
Go-Live Prep |  | 2022-07-27 01:00 |  |  | Review the following with Client to make sure they review prior to upgrade (confirmation of these are tasks on day of live) • Any 3rd party software that is used to monitor and/or track database schema changes, performance or other types of changes or monitoring should be disabled and software is not present in memory during the upgrade processes. Likewise, if there are performance issues occurring these tools should be disabled completely while Altera resources are reviewing these events. • Any backup processes that will automatically execute during the same time as the upgrade should be reviewed to determine if the process could be scheduled before or after the upgrade is completed. These processes may introduce a performance degradation related to SAN I/O. | Suhel Sumra |  | Not Applicable
Go-Live Prep |  | 2022-07-27 01:00 |  |  | Remind client that all PhysDoc documents in the Physician WorkQueues must be addressed prior to downtime. | Suhel Sumra |  | In Progress | If new ClinDoc implementation
Go-Live Prep |  | 2022-07-27 01:00 |  |  | Remind client that if live on v20 ClinDoc notes need to be closed prior to the upgrade or client will not be able to access post live. | Suhel Sumra |  | In Progress | If new ClinDoc implementation
Go-Live Prep |  | 2022-07-27 01:00 |  |  | Remind client that FDB Inventory should be cleaned up prior to live with FDB Cloud Connector | Suhel Sumra |  |  | Latest FDB update will be done in
Go-Live Prep |  | 2022-07-27 01:00 |  |  | If the client has Zetafax, they should clean out the print queue before the upgrade. If this is not done, and there are issues with the Zetafax printer, the queue will need to be cleared. | Suhel Sumra |  | Not upgraded | Not upgraded yet to 17.5
Go-Live Prep |  | 2022-07-27 01:00 |  |  | If client utilizes Imprivata, the client will need to verify on the local browser that they are not using the save login info with Auto Load function. The system tries the browser login and then the Imprivata login and they butt heads. | Suhel Sumra |  | No
Go-Live Prep |  | 2022-07-27 01:00 | #N/A |  | Ensure there is adequate space for database growth during the upgrade (check the available space a few days before the live upgrade). This check should look at all servers including the Report Server. | Chon Phuong |  | In Progress | Complete at least 1 week prior to Upgrade. There should be enough LUN storage allocated for 25% growth for both Production and Report DBs. If the database is configured to auto-grow and the database maximum size will accommodate up to 25% growth, this should be fine. .
Go-Live Prep |  | 2022-08-03 01:00 | #N/A |  | Communicate go-live procedures to end user groups: When to begin using system, who to call for help, etc. | Client / Suhel Sumra |  | Patsy Floyd | Complete at least 1 week prior to Upgrade
Go-Live Prep |  | 2022-08-03 01:00 | #N/A |  | Help Desk Preparedness - Help Desk trained and/or instructed on who to call for what types of issues. Help Desk has who to call list, Help Desk numbers provided, issue tracking procedures in place. | Client / Suhel Sumra |  | In Progress | Complete at least 1 week prior to Upgrade
Go-Live Prep |  | 2022-08-03 01:00 |  |  | Determine if client has a fully qualified AD users group for validation | Hosting (Citrix Resource) Robert Acevedo
Milestone |  |  |  |  | Milestone - Day of Go Live Activities
Day of Go Live |  | 2022-08-09 14:00 | 1 | 1 hr | Check PIU to OneContent queues to ensure there is no backlog. Restart anything as necessary. | Client |  |  | This is important if the client is switching to new OneContent servers, if not remove this task
Day of Go Live |  | 2022-08-09 14:00 | 3 | 3 hrs | All business operations complete (Financial and Business office) | Client
Day of Go Live |  | 2022-08-09 14:00 |  | 1 hr | Confirm providers have addressed all PhysDoc documents in their workqueues | Client |  |  | If new ClinDoc implementation.
Day of Go Live |  | 2022-08-09 14:00 |  | 1 hr | Copy ClinDoc templates to a shared location for publishing in Production post-upgrade | Client |  |  | If new ClinDoc implementation.
Day of Go Live |  | 2022-08-09 16:00 |  | 15 mins | Confirm any 3rd party software that is used to monitor and/or track database schema changes, performance or other types of changes or monitoring should be disabled and software is not present in memory during the upgrade processes. Likewise, if there are performance issues occurring these tools should be disabled completely while Altera resources are reviewing these events | Client |  |  | Hosting / NA
Day of Go Live |  | 2022-08-09 21:45 | 1 | 1 hr | Print out orders for in-house patients if necessary | Client |  |  | Follow your normal downtime process; Customer determines duration.
Day of Go Live |  | 2022-08-09 21:45 | 1 | 1 hr | Prepare for downtime. Print Census etc. and distribute to support downtime. | Client |  |  | Follow your normal downtime process; Customer determines duration.
Day of Go Live |  | 2022-08-09 21:45 | 2 | 2 hrs | Generate eMAR Backups | Client |  |  | Automatic eMars - will have already processed automatically, this step is printing of hard copy for staff prior to prepare for downtime. *Time so this step is finished before system shutdown
Day of Go Live |  | 2022-08-09 21:45 | 1 | 1 hr | Nursing Staff to print out EMARs for patients | Client - Nursing Staff
Day of Go Live |  | 2022-08-09 22:45 | 15 | 15 mins | Confirm no queued messages to One Content in Paragon print routing. | Client
Day of Go Live |  | 2022-08-09 22:45 | 1 | 1 hr | Put dispensing machines on override | Client - Pharmacy |  |  | Needs to be timed so it completes prior to Shutdown
Day of Go Live |  | 2022-08-09 22:45 |  |  | Complete Full database back up | Remote Hosting DBA Team
Go-Live Shutdown |  | 2022-08-09 23:45 | 5 | 5 mins | Start manual census - downtime | Client |  |  | Manual procedure to handle ADTs, Customer to follow internal process
Go-Live Shutdown |  | 2022-08-09 23:45 | 5 | 5 mins | Tracking Boards - log out both ER and ORM | Client |  |  | (This step must be completed if customers have tracking boards set to auto-login; otherwise, they will log right back in after they are removed from the system)
Day of Go Live |  | 2022-08-09 23:45 | 1 | 1 hr | Closing starts automatically- verify closing is running |  |  |  | (This may vary per Customer site, i.e. PSO, PSR & PSL may typically start before midnight. If Customer wants to change the time, will require discussing options and changing the plan.)
Day of Go Live |  | 2022-08-10 01:00 | #N/A |  | Open Conference Bridge - Altera Teams Meeting and Chat | Suhel Sumra |  |  | Create Client Meeting and Chat as well as Internal Altera Chat
Day of Go Live |  | 2022-08-10 01:00 | 30 | 30 mins | Verify Closing has completed thru job number 3. Disable daily closing windows scheduled tasks. | Paragon Tech
Day of Go Live |  | 2022-08-10 01:00 | 5 | 5 mins | Obtain approval from Client ready to start | Suhel Sumra | closing completion thru job 3
Milestone |  |  |  |  | Milestone - Go Live Shutdown
Go-Live Shutdown |  | 2022-08-10 01:00 | 5 | 5 mins | Verify all users have logged out or remove logins. | Citrix Resource
Go-Live Shutdown |  | 2022-08-10 01:00 | 5 | 5 mins | Stop interface. Verify all interfaces stay logged off and do not try to connect to Paragon. Interface transactions will queue. | Paragon Tech
Go-Live Shutdown |  | 2022-08-10 01:06 | 30 | 30 mins | Shut down the Web Server, NTIER, Reports, Rules Engine. | Paragon Tech
Go-Live Shutdown |  | 2022-08-10 01:06 | 15 | 15 mins | Shut down Processor PC and closing PC's | Paragon Tech
Go-Live Shutdown |  | 2022-08-10 01:21 | 10 | 10 mins | Set the database flag to lock out the users. Kick the users off at this time. | Paragon Tech
Go-Live Shutdown |  | 2022-08-10 01:35 | 5 | 5 mins | Complete final transaction Log | Paragon Tech |  |  | Needed if full backup is run before all users are off the system
Go-Live Shutdown |  | 2022-08-10 01:40 | 5 | 5 mins | Verify all Applications are closed and logged out. | Paragon Tech
Milestone |  |  |  |  | Milestone - Upgrade Begins
Upgrade |  | 2022-08-10 01:45 | 3 | 3 hrs | 1. Upgrades LIVE Paragon Database (Include Payroll DB if applicable) 2. For all inplace upgrades (no new hardware), the ancillary servers will all be rebooted during the upgrade by the Ancillary Tech as the servers are upgraded. Update steps above to accurately reflect your upgrade | Primary Tech |  |  | Nancy will determine the approximate time & let us know.
Upgrade |  | 2022-08-10 01:45 |  | 3 hrs | Publish (permanent) URL via Citrix in Live | Remote Hosting Citrix Engineer
Upgrade |  | 2022-08-10 01:45 | 3 | 3 hrs | Citrix server - Load all client software components, including Team Notes Form Editor, XPS Viewer - confirm paragon.ini file is correct | Remote Hosting Citrix Engineer (Hosted) |  |  | Begin as soon as all users are out of Paragon.
Upgrade |  | 2022-08-10 01:45 | 3 | 3 hrs | Reboot Citrix Servers | Remote Hosting Citrix Engineer (Hosted) |  |  | Begin as soon as all users are out of Paragon.
Upgrade |  | 2022-08-10 01:45 | 1 | 1 hr | Upgrade Closing PC, Processor PCs (confirm the Adobe Distiller has been started on closing PCH with upgrade complete) | Paragon Tech (Hosted)
Upgrade |  | 2022-08-10 01:45 | 1 | 1 hr | Upgrade MS Word 2016 on Ntier and Processor PCs | Remote Hosting HIE (Hosted)
Upgrade |  | 2022-08-10 01:45 | 1 | 1 hr | Install appropriate Microsoft Edge version on Closing PC and all Processor PCs (any workstation with Paragon installed) | Remote Hosting HIE (Hosted) |  |  | Refer to Release Guide
Upgrade |  | 2022-08-10 01:45 | 1 | 1 hr | Load Citrix Receiver Version on all Client devices. | Client |  |  | XenApp 1912 LTSR Recommended XenApp 7.15 LTSR supported
Upgrade |  | 2022-08-10 01:45 |  | 30 mins | Upgrade CDI Smartlinx to v9 | Client |  |  | If not already this version.
Upgrade |  | 2022-08-10 02:45 | 15 | 15 mins | Closing PC - make sure all Windows Scheduled Tasks point to the correct software folder | Pargaon Tech (Remote Hosted)
Upgrade |  | 2022-08-10 04:45 | 2 | 2 hrs | Paragon Techs perform system Checkout | Paragon Tech | Upgrade LIVE completes
Upgrade |  | 2022-08-10 04:45 | #N/A | 5 mins | Test Citrix login with URL in Live | Remote Hosting Citrix Engineer | Upgrade LIVE completes
Upgrade |  | 2022-08-10 04:45 |  | 30 mins | Reboot the Live Database Server If any changes made to Report or Audit Server during Upgrade then those also need to be rebooted. | Paragon Tech
Milestone |  |  |  |  | Milestone - Upgrade Finishes, System Start Up Begins
System Start Up |  | 2022-08-10 05:45 |  | 2 hrs | Altera IC's begin checkout | Altera IC's
System Start Up |  | 2022-08-10 05:45 | 5 | 5 mins | Start up Interface services with Client approval | Paragon Tech
System Start Up |  | 2022-08-10 05:45 | 5 | 5 mins | Start up Paragon Image Upload service with Client approval | Paragon Tech
System Start Up |  | 2022-08-10 05:45 | 5 | 5 mins | Startup Processor PC | Client
System Start Up |  | 2022-08-10 05:45 | 5 | 5 mins | Startup Processor Print Spooler | Client
System Start Up |  | 2022-08-10 05:45 | 5 | 5 mins | Enable Validation AD Group for validation | Remote Hosting Citrix Engineer (Hosted)
Upgrade |  | 2022-08-10 05:45 | 30 | 30 mins | Validation of application launches | Client | Upgrade LIVE completes
Upgrade |  | 2022-08-10 05:45 |  | 1 hr | Import PhysDoc Macros for ClinDoc | Primary Tech |  |  | If new ClinDoc Implementation
Downtime Build |  | 2022-08-10 05:45 | 1 | 1 hr | Analysts - Update database with any table changes . ***If changes are not in the current LIVE database, they will not be there at Go-LIVE. Any build done in TEST that is needed in Production will have to be rebuilt during this step. Clinical Doc Note Types - Acute; Clin Doc Invalidation Reasons; ILE Document Sets (ClinDoc); WSS updates | Client | * Dependency Validation of application launches
Upgrade |  | 2022-08-10 05:45 | #N/A | 1 hr | Import Clindoc Templates and Activate in OBS Manager | Client |  |  | If new CllinDoc Templates
Upgrade |  | 2022-08-10 05:45 | #N/A | 1 hr | (After Clindoc Templates are imported) Run IIS reset | Paragon Tech |  |  | If new CllinDoc Templates
Milestone |  |  |  |  | Client Checkout Client team performs app check out once notified apps are available |  |  |  | Super Users are cleared to log in to do a quick validation
Checkout |  | 2022-08-10 07:45 | 10 | 10 mins | Log into any of the devices and start any necessary apps/services that require manual intervention (e.g. DataCaptor, Pharmacy FAX Imaging, etc.) | Client
Checkout |  | 2022-08-10 07:45 |  | 15 mins | Reboot the Domain Controllers, especially if using Imprivata, after the upgrade has been completed. | Client
Checkout |  | 2022-08-10 07:45 |  | 10 mins | Clear ALL Cache before beginning checkout | Client
Checkout |  | 2022-08-10 07:45 | 15 | 15 mins | Verify reports are printing and populating | Client
Checkout |  | 2022-08-10 07:45 | 15 | 15 mins | Clinical Care Station - Review | Client
Checkout |  | 2022-08-10 07:45 | 10 | 10 mins | General Ledger - Review | Client
Checkout |  | 2022-08-10 07:45 | 10 | 10 mins | Accounts Payable - Review | Client
Checkout |  | 2022-08-10 07:45 | 10 | 10 mins | Materials Management - Review | Client
Checkout |  | 2022-08-10 07:45 | 10 | 10 mins | Fixed Assets - Review | Client
Checkout |  | 2022-08-10 07:45 | 10 | 10 mins | Medical Records - Review | Client
Checkout |  | 2022-08-10 07:45 | 10 | 10 mins | Medical Records - create CCDA from medical records. | Client
Checkout |  | 2022-08-10 07:45 | 30 | 30 mins | Validate coding - transactions are crossing from 3M to Paragon | Client
Checkout |  | 2022-08-10 07:45 | 30 | 30 mins | Validate that PIU documents are coming into One Content. | Client
Checkout |  | 2022-08-10 07:45 | 10 | 10 mins | Call the Registration dept to complete a registration on a LIVE patient. Get pt name, Acct # and MRN. Email this information to the validation team. | Client
Checkout |  | 2022-08-10 07:45 |  | 10 mins | Validate that a provider can place an electronic prescription | Client
Checkout |  | 2022-08-10 07:45 | 45 | 45 mins | Interface Validation | Client
Checkout |  | 2022-08-10 07:45 | 10 | 10 mins | Validate inbound and outbound connections are functional | Client
Checkout |  | 2022-08-10 07:45 | 10 | 10 mins | Validate ADT transactions are crossing to downstream systems | Client
Checkout |  | 2022-08-10 07:45 | 10 | 10 mins | Validate PCH is functional: | Client
Checkout |  | 2022-08-10 07:45 | 10 | 10 mins | Clinical Care Station - Add Patient Education/Validate patient education posting in patient profile. | Client
Checkout |  | 2022-08-10 07:45 | 10 | 10 mins | Registration - Facesheets printing | Client
Checkout |  | 2022-08-10 07:45 | 30 | 30 mins | Validate ILE scanning is functional - contact Registration and ask them to try the ILE scanning. | Client
Checkout |  | 2022-08-10 07:45 | 15 | 15 mins | Order Management- Review | Client
Checkout |  | 2022-08-10 07:45 | 10 | 10 mins | Validate all integration points, Eligibility, …. | Client
Checkout |  | 2022-08-10 07:45 | 20 | 20 mins | Validate orders are crossing to Pharmacy | Client
Checkout |  | 2022-08-10 07:45 | 30 | 30 mins | Radiology & PACS launch Validation | Client
Checkout |  | 2022-08-10 07:45 | 30 | 30 mins | Forms routing is validated - Lab labels and registration packets printing | Client
Checkout |  | 2022-08-10 07:45 | 15 | 15 mins | Operating Room Management- Review | Client
Checkout |  | 2022-08-10 07:45 | 15 | 15 mins | Pharmacy- Review | Client
Checkout |  | 2022-08-10 07:45 | 15 | 15 mins | Medication Administration- Review | Client
Checkout |  | 2022-08-10 07:45 | 15 | 15 mins | Validate rules are firing- rules engine | Client
Checkout |  | 2022-08-10 07:45 | 15 | 15 mins | PCH - One Content med records - Review | Client
Checkout |  | 2022-08-10 07:45 | 10 | 10 mins | Validate Phy doc records flow over to OneContent | Client
Checkout |  | 2022-08-10 07:45 | 10 | 10 mins | Validate inbound and outbound CCD | Client
Checkout |  | 2022-08-10 07:45 | 15 | 15 mins | Patient Management - Review | Client
Checkout |  | 2022-08-10 07:45 | 10 | 10 mins | Resource Scheduling - Review | Client
Checkout |  | 2022-08-10 07:45 | 15 | 15 mins | Validate Paragon Connect Service is processing transactions | Client
Backload |  | 2022-08-10 07:45 | 2 | 2 hrs | Back loading Reg/Sched - enter all of the inpatient ADTs for the current system date before running closing*CRITICAL TASK | Client |  |  | Need to verify with customer how long this step will take
Backload |  | 2022-08-10 07:45 | 2 | 2 hrs | Enter downtime patient documentation (Pharmacy, Nursing, etc.) Document in patient profile >allergies, home meds, advanced directive, family history, social history | Client - Nursing Staff |  |  | Need to verify with customer how long this step will take
Milestone |  |  |  |  | Milestone - Paragon - Allow all users access /Transition to support
Go Live |  | 2022-08-10 10:00 | TBD *See task | TBD *See task | If applicable, complete remaining daily Closing jobs (time needs to be decided during activation planning meetings and manually adjusted in the plan) | Paragon Tech
|  | 2022-08-10 10:00 |  | 10 mins | Enable All User Community Users Icon for PROD | Remote Hosting Citrix Engineer (Hosted)
Go Live |  | 2022-08-10 10:00 | 15 | 15 mins | Allow all users access | Client
Post Go Live |  | 2022-08-10 11:45 | #N/A | 15 mins | Support Go-Live Activities | Altera Team / Hosting PM / Hosting Citrix Engineer
Post Go Live |  | 2022-08-11 09:00 | 20 | 20 mins | Ensure nightly closing runs properly (On next business day) at 9AM | Client
Post Go Live |  | 2022-08-11 09:00 | 20 | 20 mins | Validate client backup procedures are running properly (On next business day ) at 9AM | Client (on Prem) / Altera Hosting PM (Hosted)
Post Go Live |  | 2022-08-11 08:15 |  | 30 mins | Post Go-Live Problem Resolution (Daily until Transition) | All
Post Go Live |  | 2022-08-12 17:00 | 30 | 30 mins | Transition to National Support | All |  |  | End of day for Paragon applications except ClinDoc if net new ClinDoc implementation.
Drop Down
| 5 mins | 5
| 10 mins | 10
| 15 mins | 15
| 20 mins | 20
| 30 mins | 30
| 45 mins | 45
| 1 hr | 1
| 1 hr | 1
| 2 hrs | 2
| 3 hrs | 3
| 4 hrs | 4
| 5 hrs | 5
| 6 hrs | 6
| 7 hrs | 7
| 8 hrs | 8
| 9 hrs | 9
| 10 hrs | 10
Note on C1: %USERNAME%: Enter Go Live date and Shut down start time here

## Check List
Topic | Response | Notes
Are Certificates current and bound? | Done
Is there a non-standard backup process in place, e.g., VEEAM? | No | Hosting client, standard back-up process (VEEAM)
What version is ZetaFax? | 17.1.1206 | Not on Supported Version
Is there a new Patient Education server with a BDI feed to OneContent? | No
Browser selected for Clinicals? | Edge
Confirming Use and Testing of Key Apps & 3rd Party Software (Some Located on Pre-Req Checklist)
Any issue with the Lab processor? | No
Any issue with nightly closing? | No
Aware and trained on the new Patient Discharge Instructions process? | Yes
OneContent Pharmacy Fax Imaging (Backoffice Baseline)? | No
Using Unified Task List? (OneContent) | No
Using Imprivata? Which version? | No
Using Nuance Dragon or MModel? Which version? | Nuance | Version:
Tested Direct Messaging, TEST and LIVE? | Yes | Tested in Test environment
Tested PACS? Launch from PCH? | No | No Test environment
Using CarePort? | No
Was the DNS Request made for HW Migration? | No
Does the customer use IMS? | Not Sure | Need to check & confirm
Using Clinician Mobile? | Yes
Downtime Registration being used for Activation? | No
Using Altera Compliance Advisor? | Yes
Clinic Integration? | No
Is the customer multi-facility? (More than 1 registering organization) | No
Is the customer multi-corporation? (General Financials) | No
Use FollowMyHealth? | Yes
If new hardware, was a case entered for FMH support to cutover to new servers at live? | No
Use FHIR and connected to MyLinks? | Not Sure | Did use in the past but not sure if this is being used currently.
Does the customer have Paragon Practice Management | No
Have reports been tested and working? (Daily, weekly reports, PCH Reports) | No | Not tested all the repports.

## Resource Planning
Domain | Day 1: Go Live Support – From Users Online to 5pm Eastern first day 08/10/2022 | Day 1: First night of Go Live, 5 PM - 8 AM | Day 2: Second day Go Live, 8 AM – 5 PM 08/11/2023 | Day 2: Second night Go Live, 5 PM - 8 AM | Day 3: Third day Go Live, 8 AM – 5 PM 08/12/2022 | Day 3: Third night Go Live
Project Manager | Suhel Sumra | Support | Suhel Sumra | Support | Suhel Sumra | Transitioned to Support
ClinDoc IC | Anita Bennett | CRITICAL Cases only to Support | Anita Bennett | CRITICAL Cases only to Support | Anita Bennett | Transitioned to Support
Clinical IC | Ketsia Simeus | Support | Ketsia Simeus | Support | Ketsia Simeus | Transitioned to Support
ORM IC | Nikita Mathur | Support | Nikita Mathur | Support | Nikita Mathur | Transitioned to Support
Lab/Rad IC | Catherine Garner (On Call) | Support | Catherine Garner (On Call) | Support | Catherine Garner (On Call) | Transitioned to Support
RevCycle IC | Sharon Thomas-Moore | Support | Sharon Thomas-Moore | Support | Sharon Thomas-Moore | Transitioned to Support
Gen Fncl IC | Fredy Ortegon | Support | Fredy Ortegon | Support | Fredy Ortegon | Transitioned to Support
Pharmacy IC & Rules Engine | Trina Daywalt | Support | Trina Daywalt | Support | Trina Daywalt | Transitioned to Support
Interface Analyst | Ashwini Patil (On Call) | Support | Ashwini Patil (On Call) | Support | Ashwini Patil (On Call) | Transitioned to Support
Tech Post Live | Heather Hosier | Support | Heather Hosier | Support | Heather Hosier | Transitioned to Support

## Standalone Fixes
WI | Description | Case # | Delivered to TEST | Installed in PROD
WI769726 | During a Discharge Med Recon if an Inpatient Order is continued, it will display twice on the PCH sidebar with incorrect frequencies. The data in the Home Medication table is correct however due to the Stored Procedure calling sidebar data it is displayed wrong. |  | Yes

## Go Live Issues List
Date Opened | Product, App, and/or Module | Category | Activation Related (Y only) | Status | Priority | Enhancement (Y/N) | Issue Description | Client Case # (if applicable) | Allscripts Case # | Originated by | Assigned to | Expected Resolution Date | Closed Date (date only) | Status Update/Comments/Resolution
Note on B1: Enter the name of the product, application and/or module associated with the issue.
Note on C1: Enter the type of issue. For example, Pharmacy issue, Lab issue, procedural, resource, or operational.
Note on D1: Complete this column ONLY if this is an issue brought to your attention during Activation/Go Live.
Note on E1: Enter the status of the issue. For example, “Open” or “Closed.”
Note on F1: Enter the resolution priority for the issue, represented by an alpha legend. The following four priorities are available: • GLB = Go-Live Blocking. A critical issue needs resolution in order for the client to Go-Live and has a direct impact on the activation date. • C = Critical. A critical issue needs resolution immediately and has a direct impact on the activation date. • H = High. A high-priority issue has a direct impact on a milestone, and needs to be resolved in a defined timeframe in order to meet the scheduled milestone date. • M = Medium. A medium-priority issue has an indirect impact on milestones, and any resolution should be scheduled to fit within project commitments. • L = Low. A low-priority issue does not have an impact on milestones, and although issues with this status should be resolved, they may be handled at a future time.
Note on H1: Enter a short description of the issue.
Note on K1: Enter the name of the individual who identified the issue.
Note on L1: Enter the name of the team or individual responsible for resolving the issue.
Note on M1: Enter the date that the issue needs to be resolved by in order to move forward or prevent delays.
Note on N1: Enter the actual close date of the issue.
Note on O1: Enter the status, progress and/or resolution of the issue. Comment should be a one or two word sentence with dates, and can include a history of the issue.

## Lessons Learned
Lessons Learned from other Clients that has gone LIVE with Paragon v20.1
# | Topic | Case / KB | Description | Responsibility | Notes
1 | Project Managers | N/A | Project had 3 project managers over the course of the project.
2 | Rules Engine | KB1519219 | Rules Engine post installation steps were not completed. The vocabularies and policies import should be completed during validation. (Paragon.Rule.Deployment.exe - need updated vocabularies and policies loaded C:\Program Files\Allscripts\Paragon BizTalk Rules\Paragon.Rule.Deployment.exe | Client | Automate to check # of rules built in test match live.
3 | FDB | KB1543829 | FDB Inventory should be cleaned up prior to live with FDB Cloud Connector | Client | Found post live
4 | Custom Reports |  | If the client has any custom reports, they should run them against the report server to validate. Western Reserve did not test, and when we went live the custom report DB file that holds the custom reports was not there and it would not work. Hosting is still working on this issue. | Client / Altera | Tasks were missed in the project plan. With new hardware, every report needs to be pointed to new instance. Testing custom reports should be part of every upgrade.
5 | ClinDoc |  | ClinDoc notes need to be closed prior to the upgrade or client will not be able to access post live. | Client
6 | Zetafax |  | If the client has Zetafax, they should clean out the print queue before the upgrade. If this is not done, and there are issues with the Zetafax printer, the queue will need to be cleared. | Client | Need to clear the Zetafax queue prior to downtime.
7 | Imprivata |  | If client utilizes Imprivata, the client will need to verify on the local browser that they are not using the save login info with Auto Load function. The system tries the browser login and then the Imprivata login and they butt heads. | Client | Setting on the local workstation
8 | 3rd Party |  | Client must coordinate the upgrade testing and live with all 3rd Party applications. | Client | Specifically Change Healthcare needs to be notified a week in advance. They need to point to new IP address and open firewalls.
9 | Mobile Apps |  | Both Paragon Clinician Mobile and Paragon Mobile Specimen Collenction will use new URLs when new hardware is part of the upgrade. These URLs should be tested and rolled out to end users. | Client | TC's need to provide URLs as soon as environments are built. Providers need to put new URL in their phone. This needs to be tested. Add to activation and project plans.
10 | Lab Application |  | Client has experienced extreme slowness with the lab application as well as deadlocks. o Found blocking on the DB that they are still trying to track down o Found multiple stored procedures that have had to be recompiled o Changes to Gandalf that were needed | Altera | Development. It is being backported to PR1 and PR2. Will be GA with PR3.
11 | Webview2 Install |  | Webview2 install was missed - add check list of servers to check out for Paraogn Tech | Altera | Anything that has Paragon loaded should have WebView2 loaded. Validate with Citrix.
12 | General Ledger |  | if site is hosted, KMS license installed from the client provides version of Excel to be used in citrix. Errors can occur if the end users trys to use a different version | Client | Hosted clients only
13 | ClinDoc |  | Signed Clindoc notes are not making it to Image Routing to go to One Content – Trina found that they actually had to go in and print a note for it to then started going to OC. Trina should have this on her list. | Altera | Check with Trina for details.
14 | CCS |  | Assessment error – libParagonReports – Shari found Parreport datasource Connection string by adding - ApplicationIntent=READONLY and Shari unchecked 'Log in using these credentials, but then try to impersonate the user viewing the report' From SDS_PARREPORT. | Altera | Check with Shari - is this just WRH or all clients for 22.x?
15 | Hosting |  | HIE verify all new servers are in CyberArk and your clients can log into them. | Altera Hosting | Hosted clients only. Add to activation plan.
16 | Hosting |  | HIE to power off all old servers from previous version | Altera Hosting | Hosted clients only. Add to activation plan.
17 | Hosting |  | HIE should send all firewall changes for the new servers to be duplicated. Examples: DI, GHX, other 3rd party vendors. Client should validate in pre-prod that all connections complete | Altera Hosting/ Client | Hosted clients only. Add to activation plan. New hardware only.
18 | Hosting |  | New process for Backups night of the upgrade. Hosting PM should take care of this: o Put in request to Kabir to turn off VEEAM at like 5 pm on day before the upgrade o Put in request to DBA team/Darlene to schedule DBA to install SQL backups and schedule the backup for 7 or 8 pm and notify the TC to run tLogs. o Day of upgrade have Kabir turn VEEAM back on o Day of upgrade have DBA disable SQL backups | Altera Hosting | Melissa to document actual steps to add to plans.
19 | Hosting |  | Citrix engineer verify if RAM/LAM is used with the sites PACS. If so verify RAM is installed on Citrix and Client verifies LAM is installed on the local PCs with the PACS software and launch works | Altera Hosting/ Client | Hosting PM and TAM for PACS
20 |  |  | HIE/Hosting PM needs to - Setup monitoring for new servers for v22 - Inform the QTS DBA, Windows, and Upgrades teams of the new SQL Servers when they go live - Have SysCare updated with new servers and set old servers to pre-decom - Send server list to power down and decom to Jay Bailey |  | Steps that hosting needs to complete. Add to project plan.
21 | Lab Application | KB1544015 | Paragon Laboratory and Radiology Processor after an upgrade.
22 |  | WI771555 | Everything was being sent to Zetafax as default printer. Rafy tried to fix, but it would not stay. | Client
23 | Zetafax |  | Zetafax upgrade prior to activation. | Altera
24 |  | WI745259 | Not working 22.1 CU1 PR1 - Lab printer is not defaulting to workstation default printer. It's still using Citrix Default printer
25 |  | INC19387120/ INC19387430 (PRB15046967) / CS18798691 | MI Cases - Users cannot log into system | Altera | Services and Support to have instructions added to the Paragon 22 upgrade documentation

## Sheet1
|  | 2022-08-10 01:00 |  | Eastern Time Zone
Phase | Status | Approximate Start Time | FORMULA | Estimated Duration | Task Name | Responsibility | Dependency | Comments/ Notes
Go-Live Prep |  | 2022-07-20 01:00 | #N/A |  | Discuss SSIS data base and custom reports. If site has them they need a backup of the reports and the SQL data base moved over from current prod to pre prod | Altera PM
Go-Live Prep |  | 2022-07-20 01:00 | #N/A |  | Verify PI Reporting has been tested | Altera PM
Go-Live Prep |  | 2022-07-20 01:00 | #N/A |  | Discuss plan for Closing jobs: What time will it be run? How many jobs will be completed before the downtime? Will there be any jobs to be completed after the system is back up? | Altera PM |  | HPF – Transfer FMR – starts at 1am and finishes around 5;15am MAR – Transfer MedAdmin – starts at 3:15am and finishes around 5am COE- Transfer CPOE Orders – starts at 1am and finishes in 5-10 minutes MRR – Transfer MedRecon – starts at 1am and finishes about 1:15am PAT – Transfer Patient Profile – starts at 7:30am and finishes in a couple minutes Paragon Tech will run the jobs manually which are not run during closing & will start manually.
Go-Live Prep |  | 2022-07-20 01:00 |  |  | Confirm PACS has been tested and any steps necessary to activate (i.e. rebooting, recycling, etc.) have been added to their live steps. | Altera PM |  | To be completed at least 3 weeks prior to activation
Go-Live Prep |  | 2022-07-20 01:00 |  |  | Confirm whether any additional IT work or upgrades are planned during downtime for the upgrade. | Altera PM |  | Goal is to not have any additional activities that are not required or related to the upgrade.
Go-Live Prep |  | 2022-07-27 01:00 | #N/A |  | Set up call with Primary Tech to compare timing and software, bundles and WI to be installed. If Remote Hosted, include Hosting PM and Citrix resource. | Altera PM |  | Suhel to check notes for standalone
Go-Live Prep |  | 2022-07-27 01:00 | #N/A |  | Open Change Request for Production upgrade in ServiceNow (Chon will make sure blackout is in place when putting it in change request) | Chon Phuong |  | Chon will have RFC by 8/5/2022
Go Live Prep |  | 2022-07-27 01:00 |  |  | Confirm the Citrix Receiver version on the client devices are aligned with Paragon requirements. (See Hardware requirements document from Altera Central.) | Client |  | Need to check with client
Go-Live Prep |  | 2022-07-27 01:00 | #N/A |  | Client to Ensure they have access to all areas that have tracking boards - will need to power off before the upgrade starts | Client |  | Needed for shutting down tracking boards if customers have tracking boards set to auto-login; otherwise, they will log right back in.
Go-Live Prep |  | 2022-07-27 01:00 | #N/A |  | Review standalone fix list and record actual installs to those delivered. Provide final list to Primary Tech. Confirm the list with the Client as well. | Altera PM |  | Complete at least 2 weeks prior to Upgrade, no later than 4 business days prior to upgrade.
Go-Live Prep |  | 2022-07-27 01:00 |  |  | Notify VEEM Team of new production server | Remote Hosting HIE |  | Remove if On Premise
Go-Live Prep |  | 2022-07-27 01:00 |  |  | Review the following with Client to make sure they review prior to upgrade (confirmation of these are tasks on day of live) • Any 3rd party software that is used to monitor and/or track database schema changes, performance or other types of changes or monitoring should be disabled and software is not present in memory during the upgrade processes. Likewise, if there are performance issues occurring these tools should be disabled completely while Altera resources are reviewing these events. • Any backup processes that will automatically execute during the same time as the upgrade should be reviewed to determine if the process could be scheduled before or after the upgrade is completed. These processes may introduce a performance degradation related to SAN I/O. | Altera PM
Go-Live Prep |  | 2022-07-27 01:00 |  |  | Contact all 3rd partys a week prior to the upgrade. Provide them with the new server names and IP address. Make sure no firewall changes are needed or parameter changes for new servers. | Client | No Application | If new Hardware
Go-Live Prep |  | 2022-07-27 01:00 |  |  | Remind client that all PhysDoc documents in the Physician WorkQueues must be addressed prior to downtime. | Altera PM |  | If new ClinDoc implementation
Go-Live Prep |  | 2022-07-27 01:00 |  |  | Remind client that if live on v20 ClinDoc notes need to be closed prior to the upgrade or client will not be able to access post live. | Altera PM |  | If new ClinDoc implementation
Go-Live Prep |  | 2022-07-27 01:00 |  |  | Remind client that FDB Inventory should be cleaned up prior to live with FDB Cloud Connector | Altera PM |  | If new FDB Cloud Connector
Go-Live Prep |  | 2022-07-27 01:00 |  |  | If the client has Zetafax, they should clean out the print queue before the upgrade. If this is not done, and there are issues with the Zetafax printer, the queue will need to be cleared. | Altera PM |  | Not upgraded yet to 17.5
Go-Live Prep |  | 2022-07-27 01:00 |  |  | If client utilizes Imprivata, the client will need to verify on the local browser that they are not using the save login info with Auto Load function. The system tries the browser login and then the Imprivata login and they butt heads. | Altera PM
Go-Live Prep |  | 2022-07-27 01:00 |  |  | Remind client that both Paragon Clinician Mobile and Paragon Mobile Specimen Collenction will use new URLs when new hardware is part of the upgrade. These URLs should be tested and rolled out to end users. | Altera PM | Not Applicable
Go-Live Prep |  | 2022-07-27 01:00 |  |  | Educate Client Base on Citrix Servers running all applications | Altera Hosting Citrix Resource | Not Applicable | Remove if on premise.
Go-Live Prep |  | 2022-07-27 01:00 |  |  | Discuss with Client the need to complete the following tasks Post upgrade. • A SQL Server reboot should be performed after an upgrade is performed. • Verify that the PCH Server's application pool recycle time is set correctly after each PCH install. | Altera Hosting PM | Not Applicable
Go-Live Prep |  | 2022-07-27 01:00 | #N/A |  | Ensure there is adequate space for database growth during the upgrade (check the available space a few days before the live upgrade). This check should look at all servers including the Report Server. | Chon Phuong |  | Complete at least 1 week prior to Upgrade. There should be enough LUN storage allocated for 25% growth for both Production and Report DBs. If the database is configured to auto-grow and the database maximum size will accommodate up to 25% growth, this should be fine. .
Go-Live Prep |  | 2022-08-03 01:00 | #N/A |  | Communicate go-live procedures to end user groups: When to begin using system, who to call for help, etc. | Client / Suhel Sumra |  | Complete at least 1 week prior to Upgrade
Go-Live Prep |  | 2022-08-03 01:00 | #N/A |  | Help Desk Preparedness - Help Desk trained and/or instructed on who to call for what types of issues. Help Desk has who to call list, Help Desk numbers provided, issue tracking procedures in place. | Client / Suhel Sumra |  | Complete at least 1 week prior to Upgrade
Go-Live Prep |  | 2022-08-03 01:00 | #N/A |  | Provide remote access to desktops for onsite Altera resources | Client | Not Applicable | Complete no later than 4 business days prior to Go Live *This will be applicable per upgrade complexity.
Go-Live Prep |  | 2022-08-03 01:00 |  |  | Determine if client has a fully qualified AD users group for validation | Hosting (Citrix Resource) Robert Acevedo
Go-Live Prep |  | 2022-08-03 01:00 |  |  | Provide Start Time and Typical Duration of Daily Paragon back up process | Remote Hosting VEEAM Team | Not Applicable
Go-Live Prep |  | 2022-08-03 01:00 |  |  | Communicate LogicMonitor, Daily Backup (if applicable) Blackouts in place | Remote Hosting HIE (Hosted) | Not Applicable | Send notification to IMS
Go-Live Prep |  | 2022-08-03 01:00 |  |  | Note: All ancillary servers will be rebooted as part of the Hardware Migration / Microsoft Updates. | Paragon Tech (On Prem) / Hosting (Hosted) | Not Applicable | Delete if the upgrade does not inlcude a hardware migration.
Go-Live Prep |  | 2022-08-03 01:00 |  |  | HIE should send all firewall changes for the new servers to be duplicated. Examples: DI, GHX, other 3rd party vendors. Client should validate in pre-prod that all connections complete | Hosting Team | Not Applicable | Delete if the upgrade does not inlcude a hardware migration.
Go-Live Prep |  | 2022-08-03 01:00 |  |  | HIE verify all new servers are in CyberArk and client can access. | Hosting Team | Not Applicable | Delete if the upgrade does not inlcude a hardware migration.
Go-Live Prep |  | 2022-08-03 01:00 |  |  | HIE/Hosting PM: - Setup monitoring for new servers for v22 - Inform the QTS DBA, Windows, and Upgrades teams of the new SQL Servers when they go live - Have SysCare updated with new servers and set old servers to pre-decom - Send server list to power down and decom to Jay Bailey | Hosting Team | Not Applicable | Delete if the upgrade does not inlcude a hardware migration.
Go-Live Prep |  | 2022-08-03 01:00 |  |  | If site currently uses PACS launch to a 3rd party. Verify launch works in pre-test and pre-prod |  | Not Applicable | Delete if the upgrade does not inlcude a hardware migration.
Milestone |  |  |  |  | Milestone - Day of Go Live Activities
Day of Go Live |  | 2022-08-09 14:00 | 1 | 1 hr | Check PIU to OneContent queues to ensure there is no backlog. Restart anything as necessary. | Client |  | This is important if the client is switching to new OneContent servers, if not remove this task
Day of Go Live |  | 2022-08-09 14:00 | 3 | 3 hrs | All business operations complete (Financial and Business office) | Client
Day of Go Live |  | 2022-08-09 14:00 |  | 1 hr | Confirm providers have addressed all PhysDoc documents in their workqueues | Client |  | If new ClinDoc implementation.
Day of Go Live |  | 2022-08-09 14:00 |  | 1 hr | Copy ClinDoc templates to a shared location for publishing in Production post-upgrade | Client |  | If new ClinDoc implementation.
Day of Go Live |  | 2022-08-09 16:00 |  | 15 mins | Confirm any 3rd party software that is used to monitor and/or track database schema changes, performance or other types of changes or monitoring should be disabled and software is not present in memory during the upgrade processes. Likewise, if there are performance issues occurring these tools should be disabled completely while Altera resources are reviewing these events | Client |  | Hosting / NA
Day of Go Live |  | 2022-08-09 16:00 |  | 15 mins | Confirm any backup processes that will automatically execute during the same time as the upgrade should be reviewed to determine if the process could be scheduled before or after the upgrade is completed. These processes may introduce a performance degradation related to SAN I/O. | Client (on Prem) or Remote Hosting | Not Applicable
Day of Go Live |  | 2022-08-09 21:45 | 1 | 1 hr | Print out orders for in-house patients if necessary | Client |  | Follow your normal downtime process; Customer determines duration.
Day of Go Live |  | 2022-08-09 21:45 | 1 | 1 hr | Prepare for downtime. Print Census etc. and distribute to support downtime. | Client |  | Follow your normal downtime process; Customer determines duration.
Day of Go Live |  | 2022-08-09 21:45 | 2 | 2 hrs | Generate eMAR Backups | Client |  | Automatic eMars - will have already processed automatically, this step is printing of hard copy for staff prior to prepare for downtime. *Time so this step is finished before system shutdown
Day of Go Live |  | 2022-08-09 21:45 | 1 | 1 hr | Nursing Staff to print out EMARs for patients | Client - Nursing Staff
Day of Go Live |  | 2022-08-09 22:45 | 15 | 15 mins | Confirm no queued messages to One Content in Paragon print routing. | Client
Day of Go Live |  | 2022-08-09 22:45 | 1 | 1 hr | Put dispensing machines on override | Client - Pharmacy |  | Needs to be timed so it completes prior to Shutdown
Day of Go Live |  | 2022-08-09 22:45 |  |  | Complete Full database back up | Remote Hosting DBA Team
Go-Live Shutdown |  | 2022-08-09 23:45 | 5 | 5 mins | Start manual census - downtime | Client |  | Manual procedure to handle ADTs, Customer to follow internal process
Go-Live Shutdown |  | 2022-08-09 23:45 | 5 | 5 mins | Tracking Boards - log out both ER and ORM | Client |  | (This step must be completed if customers have tracking boards set to auto-login; otherwise, they will log right back in after they are removed from the system)
Day of Go Live |  | 2022-08-09 23:45 | 1 | 1 hr | Closing starts automatically- verify closing is running |  |  | (This may vary per Customer site, i.e. PSO, PSR & PSL may typically start before midnight. If Customer wants to change the time, will require discussing options and changing the plan.)
Day of Go Live | 1:00 | 2022-08-10 00:15 | #N/A |  | Open Conference Bridge - Altera Teams Meeting and Chat | Altera PM |  | Create Client Meeting and Chat as well as Internal Altera Chat
Day of Go Live | 1:00 | 2022-08-10 00:15 | 30 | 30 mins | Verify Closing has completed thru job number 3. Disable daily closing windows scheduled tasks. | Paragon Tech
Day of Go Live | 1:00 | 2022-08-10 00:45 | 5 | 5 mins | Obtain approval from Client ready to start | Altera PM | closing completion thru job 3
Milestone |  |  |  |  | Milestone - Go Live Shutdown
Go-Live Shutdown |  | 2022-08-10 01:00 | 5 | 5 mins | Verify all users have logged out or remove logins. | Citrix Resource
Go-Live Shutdown |  | 2022-08-10 01:00 | 5 | 5 mins | Stop interface. Verify all interfaces stay logged off and do not try to connect to Paragon. Interface transactions will queue. | Paragon Tech
Go-Live Shutdown |  | 2022-08-10 01:06 | 30 | 30 mins | Shut down the Web Server, NTIER, Reports, Rules Engine. | Paragon Tech
Go-Live Shutdown |  | 2022-08-10 01:06 | 15 | 15 mins | Shut down Processor PC and closing PC's | Paragon Tech
Go-Live Shutdown |  | 2022-08-10 01:21 | 10 | 10 mins | Set the database flag to lock out the users. Kick the users off at this time. | Paragon Tech
Go-Live Shutdown |  | 2022-08-10 01:30 | 5 | 5 mins | Remove remaining users and kick out terminal users to lock out all new users | Client | Not Applicable
Go-Live Shutdown |  | 2022-08-10 01:35 | 5 | 5 mins | Complete final transaction Log | Paragon Tech |  | Needed if full backup is run before all users are off the system
Go-Live Shutdown |  | 2022-08-10 01:40 | 5 | 5 mins | Verify all Applications are closed and logged out. | Paragon Tech
Milestone |  |  |  |  | Milestone - Upgrade Begins
Upgrade |  | 2022-08-10 01:45 | 7 | 7 hrs | 1. Upgrades LIVE Paragon Database (Include Payroll DB if applicable) 2. For all inplace upgrades (no new hardware), the ancillary servers will all be rebooted during the upgrade by the Ancillary Tech as the servers are upgraded. Update steps above to accurately reflect your upgrade | Primary Tech |  | Nancy will determine the approximate time & let us know.
Upgrade |  | 2022-08-10 01:45 |  | 1 hr | Verify Redis is installed and configured | Primary Tech | Not Applicable
Upgrade |  | 2022-08-10 01:45 |  | 3 hrs | Publish (permanent) URL via Citrix in Live | Remote Hosting Citrix Engineer
Upgrade |  | 2022-08-10 01:45 | 3 | 3 hrs | Citrix server - Load all client software components, including Team Notes Form Editor, XPS Viewer - confirm paragon.ini file is correct | Remote Hosting Citrix Engineer (Hosted) |  | Begin as soon as all users are out of Paragon.
Upgrade |  | 2022-08-10 01:45 | 3 | 3 hrs | Reboot Citrix Servers | Remote Hosting Citrix Engineer (Hosted) |  | Begin as soon as all users are out of Paragon.
Upgrade |  | 2022-08-10 01:45 | 1 | 1 hr | Upgrade Closing PC, Processor PCs (confirm the Adobe Distiller has been started on closing PCH with upgrade complete) | Paragon Tech (Hosted)
Upgrade |  | 2022-08-10 01:45 | 1 | 1 hr | Upgrade MS Word 2016 on Ntier and Processor PCs | Remote Hosting HIE (Hosted)
Upgrade |  | 2022-08-10 01:45 | 1 | 1 hr | Install appropriate Microsoft Edge version on Closing PC and all Processor PCs (any workstation with Paragon installed) | Remote Hosting HIE (Hosted) |  | Refer to Release Guide
Upgrade |  | 2022-08-10 01:45 | 1 | 1 hr | Load Citrix Receiver Version on all Client devices. | Client |  | XenApp 1912 LTSR Recommended XenApp 7.15 LTSR supported
Upgrade |  | 2022-08-10 01:45 |  | 30 mins | Upgrade CDI Smartlinx to v9 | Client |  | If not already this version.
Upgrade |  | 2022-08-10 02:45 | 15 | 15 mins | Closing PC - make sure all Windows Scheduled Tasks point to the correct software folder | Pargaon Tech (Remote Hosted)
Upgrade |  | 2022-08-10 08:45 | 1 | 1 hr | Paragon Techs perform system Checkout | Paragon Tech | Upgrade LIVE completes
Upgrade |  | 2022-08-10 08:45 |  | 5 mins | Cycle PCH app pool | Primary Tech | Not Applicable
Upgrade |  | 2022-08-10 08:45 | #N/A | 5 mins | Test Citrix login with URL in Live | Remote Hosting Citrix Engineer | Upgrade LIVE completes
Upgrade |  | 2022-08-10 08:45 |  | 30 mins | Reboot the Live Database Server If any changes made to Report or Audit Server during Upgrade then those also need to be rebooted. | Paragon Tech
Milestone |  |  |  |  | Milestone - Upgrade Finishes, System Start Up Begins
System Start Up |  | 2022-08-10 09:15 |  | 30 mins | Altera IC's begin checkout | Altera IC's
System Start Up |  | 2022-08-10 09:45 | 5 | 5 mins | Start up Interface services with Client approval | Paragon Tech
System Start Up |  | 2022-08-10 09:45 | 5 | 5 mins | Start up Paragon Image Upload service with Client approval | Paragon Tech
System Start Up |  | 2022-08-10 09:45 |  | 5 mins | Enable the lab_event_processor task in the Processor Scheduler for Lab | Client | Not Applicable | Review KB1524607 if the customer has questions
System Start Up |  | 2022-08-10 09:45 | 5 | 5 mins | Startup Processor PC | Client
System Start Up |  | 2022-08-10 09:45 | 5 | 5 mins | Startup Processor Print Spooler | Client
System Start Up |  | 2022-08-10 09:45 | 5 | 5 mins | Enable Validation AD Group for validation | Remote Hosting Citrix Engineer (Hosted)
Upgrade |  | 2022-08-10 09:45 | 30 | 30 mins | Validation of application launches | Client | Upgrade LIVE completes
Upgrade |  | 2022-08-10 09:45 |  | 10 mins | Verify that the PCH Server's application pool recycle time is set correctly after each PCH install | Client (On Prem) or Pargaon Tech (Remote Hosted) | Not Applicable
Upgrade |  | 2022-08-10 09:45 |  | 1 hr | Import PhysDoc Macros for ClinDoc | Primary Tech |  | If new ClinDoc Implementation
Downtime Build |  | 2022-08-10 09:45 | 1 | 1 hr | Analysts - Update database with any table changes . ***If changes are not in the current LIVE database, they will not be there at Go-LIVE. Any build done in TEST that is needed in Production will have to be rebuilt during this step. Clinical Doc Note Types - Acute; Clin Doc Invalidation Reasons; ILE Document Sets (ClinDoc); WSS updates | Client | * Dependency Validation of application launches
Upgrade |  | 2022-08-10 09:45 | #N/A | 1 hr | Import Clindoc Templates and Activate in OBS Manager | Client |  | If new CllinDoc Templates
Upgrade |  | 2022-08-10 09:45 | #N/A | 1 hr | (After Clindoc Templates are imported) Run IIS reset | Paragon Tech |  | If new CllinDoc Templates
Milestone |  |  |  |  | Client Checkout Client team performs app check out once notified apps are available |  |  | Super Users are cleared to log in to do a quick validation
Checkout |  | 2022-08-10 10:45 | 10 | 10 mins | Log into any of the devices and start any necessary apps/services that require manual intervention (e.g. DataCaptor, Pharmacy FAX Imaging, etc.) | Client
Checkout |  | 2022-08-10 10:45 |  | 15 mins | Reboot the Domain Controllers, especially if using Imprivata, after the upgrade has been completed. | Client
Checkout |  | 2022-08-10 10:45 |  | 10 mins | Clear ALL Cache before beginning checkout | Client
Checkout |  | 2022-08-10 10:45 | 15 | 15 mins | Verify reports are printing and populating | Client
Checkout |  | 2022-08-10 10:45 | 15 | 15 mins | Clinical Care Station - Review | Client
Checkout |  | 2022-08-10 10:45 | 10 | 10 mins | General Ledger - Review | Client
Checkout |  | 2022-08-10 10:45 | 10 | 10 mins | Accounts Payable - Review | Client
Checkout |  | 2022-08-10 10:45 | 10 | 10 mins | Materials Management - Review | Client
Checkout |  | 2022-08-10 10:45 | 10 | 10 mins | Fixed Assets - Review | Client
Checkout |  | 2022-08-10 10:45 | 10 | 10 mins | Medical Records - Review | Client
Checkout |  | 2022-08-10 10:45 | 10 | 10 mins | Medical Records - create CCDA from medical records. | Client
Checkout |  | 2022-08-10 10:45 | 30 | 30 mins | Validate coding - transactions are crossing from 3M to Paragon | Client
Checkout |  | 2022-08-10 10:45 | 30 | 30 mins | Validate that PIU documents are coming into One Content. | Client
Checkout |  | 2022-08-10 10:45 | 10 | 10 mins | Call the Registration dept to complete a registration on a LIVE patient. Get pt name, Acct # and MRN. Email this information to the validation team. | Client
Checkout |  | 2022-08-10 10:45 |  | 10 mins | Validate that a provider can place an electronic prescription | Client
Checkout |  | 2022-08-10 10:45 | 45 | 45 mins | Interface Validation | Client
Checkout |  | 2022-08-10 10:45 | 10 | 10 mins | Validate inbound and outbound connections are functional | Client
Checkout |  | 2022-08-10 10:45 | 10 | 10 mins | Validate ADT transactions are crossing to downstream systems | Client
Checkout |  | 2022-08-10 10:45 | 10 | 10 mins | Validate PCH is functional: | Client
Checkout |  | 2022-08-10 10:45 | 10 | 10 mins | Clinical Care Station - Add Patient Education/Validate patient education posting in patient profile. | Client
Checkout |  | 2022-08-10 10:45 | 10 | 10 mins | Registration - Facesheets printing | Client
Checkout |  | 2022-08-10 10:45 | 30 | 30 mins | Validate ILE scanning is functional - contact Registration and ask them to try the ILE scanning. | Client
Checkout |  | 2022-08-10 10:45 | 15 | 15 mins | Order Management- Review | Client
Checkout |  | 2022-08-10 10:45 | 10 | 10 mins | Validate all integration points, Eligibility, …. | Client
Checkout |  | 2022-08-10 10:45 | 20 | 20 mins | Validate orders are crossing to Pharmacy | Client
Checkout |  | 2022-08-10 10:45 | 30 | 30 mins | Radiology & PACS launch Validation | Client
Checkout |  | 2022-08-10 10:45 | 30 | 30 mins | Forms routing is validated - Lab labels and registration packets printing | Client
Checkout |  | 2022-08-10 10:45 | 15 | 15 mins | Operating Room Management- Review | Client
Checkout |  | 2022-08-10 10:45 | 15 | 15 mins | Pharmacy- Review | Client
Checkout |  | 2022-08-10 10:45 | 15 | 15 mins | Medication Administration- Review | Client
Checkout |  | 2022-08-10 10:45 | 15 | 15 mins | Validate rules are firing- rules engine | Client
Checkout |  | 2022-08-10 10:45 | 15 | 15 mins | PCH - One Content med records - Review | Client
Checkout |  | 2022-08-10 10:45 | 10 | 10 mins | Validate Phy doc records flow over to OneContent | Client
Checkout |  | 2022-08-10 10:45 | 10 | 10 mins | Validate inbound and outbound CCD | Client
Checkout |  | 2022-08-10 10:45 | 15 | 15 mins | Patient Management - Review | Client
Checkout |  | 2022-08-10 10:45 | 10 | 10 mins | Resource Scheduling - Review | Client
Checkout |  | 2022-08-10 10:45 | 15 | 15 mins | Validate Paragon Connect Service is processing transactions | Client
Backload |  | 2022-08-10 10:45 | 2 | 2 hrs | Back loading Reg/Sched - enter all of the inpatient ADTs for the current system date before running closing*CRITICAL TASK | Client |  | Need to verify with customer how long this step will take
Backload |  | 2022-08-10 10:45 | 2 | 2 hrs | Enter downtime patient documentation (Pharmacy, Nursing, etc.) Document in patient profile >allergies, home meds, advanced directive, family history, social history | Client - Nursing Staff |  | Need to verify with customer how long this step will take
Milestone |  |  |  |  | Milestone - Paragon - Allow all users access /Transition to support
Go Live |  | 2022-08-10 11:45 | TBD *See task | TBD *See task | If applicable, complete remaining daily Closing jobs (time needs to be decided during activation planning meetings and manually adjusted in the plan) | Paragon Tech
|  | 2022-08-10 11:45 |  | 10 mins | Enable All User Community Users Icon for PROD | Remote Hosting Citrix Engineer (Hosted)
Go Live |  | 2022-08-10 11:45 | 15 | 15 mins | Allow all users access | Client
Post Go Live |  | 2022-08-10 11:45 | #N/A | 15 mins | Support Go-Live Activities | Altera Team / Hosting PM / Hosting Citrix Engineer
Post Go Live |  | 2022-08-11 10:00 | 20 | 20 mins | Ensure nightly closing runs properly (On next business day) at 9AM | Client
Post Go Live |  | 2022-08-11 10:00 | 20 | 20 mins | Validate client backup procedures are running properly (On next business day ) at 9AM | Client (on Prem) / Altera Hosting PM (Hosted)
Post Go Live |  | 2022-08-11 10:00 |  | 30 mins | Post Go-Live Problem Resolution (Daily until Transition) | All
Post Go Live |  | 2022-08-12 18:00 | 30 | 30 mins | Transition to National Support | All |  | End of day for Paragon applications except ClinDoc if net new ClinDoc implementation.
Drop Down
| 5 mins | 5
| 10 mins | 10
| 15 mins | 15
| 20 mins | 20
| 30 mins | 30
| 45 mins | 45
| 1 hr | 1
| 1 hr | 1
| 2 hrs | 2
| 3 hrs | 3
| 4 hrs | 4
| 5 hrs | 5
| 6 hrs | 6
| 7 hrs | 7
| 8 hrs | 8
| 9 hrs | 9
| 10 hrs | 10
Note on C1: %USERNAME%: Enter Go Live date and Shut down start time here